FLOWFIY

AI Outbound Sales Platform

₹10 LAKH  IN  3 MONTHS

Aggressive 90-Day Growth & User Acquisition Sprint

Target: 350 paying users  |  ₹5.95L MRR  |  90 days

| MONTH 1 Launch Blitz ₹3,50,000 | MONTH 2 Double Down ₹4,00,000 | MONTH 3 Close Hard ₹2,50,000 |
| --- | --- | --- |

Ayush Saha  |  Founder, Flowfiy  |  flowfiy.com  |  May 2026  |  Confidential

# 1.  The 3-Month Mindset Shift

⚡  3 months is not a compressed 9-month plan. It is a completely different strategy.

In a 9-month plan, you can afford patience — SEO, slow-burn content, organic referrals. In 3 months, you have one job: get paying users as fast as possible through channels that work in days, not months.

| Principle | 9-Month Plan | 3-Month Plan (This Doc) |
| --- | --- | --- |
| Primary channel | Balanced mix | Paid Ads + Direct Outreach (90% of budget) |
| SEO / Content | ₹1,50,000 over 9 months | CUT. Takes 4-6 months to rank. Zero ROI in 90 days. |
| Outreach volume | ~900 emails/month | 3,000+ emails/month via Flowfiy |
| Agency BD | Month 3-5 | Week 1. First priority. |
| WhatsApp outreach | Not in plan | Active from Day 1. India-native channel. |
| Founder sales | Occasional | Daily. Ayush closes deals personally. |
| Target at end | 500 users in 9 months | 350 users in 3 months |

# 2.  Budget Allocation  —  ₹10,00,000 in 90 Days

Every rupee is assigned to a specific week-level action. Nothing is vague.

| Category | Month 1 | Month 2 | Month 3 | Total |
| --- | --- | --- | --- | --- |
| Paid Ads (LinkedIn + Google) | ₹1,30,000 | ₹1,60,000 | ₹80,000 | ₹3,70,000 |
| Direct Outreach (Flowfiy + WhatsApp) | ₹25,000 | ₹25,000 | ₹20,000 | ₹70,000 |
| Agency Partnerships & BD | ₹50,000 | ₹60,000 | ₹40,000 | ₹1,50,000 |
| Product & Onboarding Fix | ₹80,000 | ₹50,000 | ₹40,000 | ₹1,70,000 |
| Freelance Sales VA | ₹0 | ₹30,000 | ₹30,000 | ₹60,000 |
| Events & PR | ₹20,000 | ₹40,000 | ₹20,000 | ₹80,000 |
| Referral Program Incentives | ₹15,000 | ₹55,000 | ₹30,000 | ₹1,00,000 |
| Operations & Legal | ₹30,000 | ₹0 | ₹0 | ₹30,000 |
| Reserve / Emergency | ₹0 | ₹30,000 | ₹40,000 | ₹70,000 |
| TOTAL | ₹3,50,000 | ₹4,00,000 | ₹2,50,000 | ₹10,00,000 |

MONTH 1 — LAUNCH BLITZ (Days 1–30) Budget: ₹3,50,000

Objective: Get to 50 paying users. Fix onboarding, launch all acquisition channels simultaneously, close the first batch personally.

Month 1 is the most important month. The channels you test here determine everything in Month 2 and 3. Speed over perfection.

## Week 1 — Foundation (Days 1–7)

Before spending a single rupee on ads, fix the product funnel. A leaking bucket wastes every marketing rupee.

| Task | Action | Cost |
| --- | --- | --- |
| Fix onboarding drop-off | Hire freelancer for 1-week sprint. Goal: user signs up → first lead list generated in under 5 minutes. Remove every friction point. | ₹25,000 |
| Set up analytics | Install PostHog. Track: signup, onboarding complete, first run, paid conversion. Know your baseline before spending on ads. | ₹0 (free tier) |
| Set up email drip | 3-email onboarding sequence: Day 0 (welcome + guide), Day 2 (tips), Day 5 (upgrade nudge). Use Loops or Resend. | ₹5,000 |
| Build comparison landing page | 1 page: 'Flowfiy vs Apollo vs Lemlist' — captures high-intent search traffic and doubles as ad landing page. | ₹15,000 |
| Start Flowfiy self-outreach | Apollo: 500 Indian agency founders searched and loaded. Flowfiy runs the first campaign. 30 emails/day from Day 1. | ₹10,000 (Apollo sub) |

## Week 2 — All Channels Live (Days 8–14)

| Channel | Setup & Action | Budget |
| --- | --- | --- |
| LinkedIn Ads — Set A | Audience: Founders + CEOs at 2-30 person marketing/web/branding agencies in India. Format: Lead Gen Form. Creative: '500 personalised cold emails in 1 hour — how?' CTA: Start Free. | ₹40,000 |
| LinkedIn Ads — Set B | Audience: Growth Heads + BD Managers. Format: Video demo ad (2-min screen recording of a real Flowfiy run). Test against Set A. | ₹30,000 |
| Google Search Ads | Keywords: 'lead generation tool India', 'AI cold email software', 'outbound sales automation India'. Target search intent only. | ₹30,000 |
| Agency BD outreach | Identify 20 digital marketing agencies in Pune, Mumbai, Bengaluru. Reach them via Flowfiy. Pitch: 'I will generate 100 qualified leads for your agency free of charge — using Flowfiy. If it works, I want a testimonial + referral deal.' | ₹5,000 |
| WhatsApp outreach | Find mobile numbers of agency founders via Google Maps, Justdial, LinkedIn. Send 15 personalised WhatsApp messages/day. Use the Flowfiy-generated email angle as the message hook. | ₹5,000 |

## Weeks 3–4 — Cut & Double (Days 15–30)

Kill any ad set with CPL > ₹1,000. Double the budget on the set with CPL < ₹600. Personally call every trial user who hasn't converted after 5 days.

| Action | Detail | Budget |
| --- | --- | --- |
| Scale winning ad set | Take the better LinkedIn set from Week 2. 2x the daily budget. | ₹25,000 |
| Personal demo calls | Every trial who hasn't converted: Ayush personally calls. 10-min call. Ask what's blocking them. Close on the call. | ₹0 |
| LinkedIn organic posts | 3 posts/week: share a real Flowfiy run result ('sent 200 cold emails, got 7 replies in 1 day'). Founder-voice only. | ₹0 |
| Legal & GST | Register GST. Privacy policy. Terms of service. Business bank account. | ₹30,000 |

| Month 1 Target | Users | MRR |
| --- | --- | --- |
| End of Day 30 | 50 paying users | ₹85,000/month |

MONTH 2 — DOUBLE DOWN (Days 31–60) Budget: ₹4,00,000

Objective: Scale from 50 to 175 users. By now you know which channel converts. Put 70% of the budget there. Add agency partnerships as a multiplier. Hire a sales VA.

⚡  Do NOT add new untested channels in Month 2. Only scale what proved ROI in Month 1.

## Scale Paid Ads — Winning Channel Only

| Action | Detail | Budget |
| --- | --- | --- |
| Scale best-performing ad | Take the top-performing LinkedIn or Google campaign from Month 1. Increase daily budget 3x. Add 2 new creative variants (different pain point angles). | ₹1,00,000 |
| Retargeting campaign | Retarget all website visitors and trial sign-ups who didn't convert. Ad copy: 'Still thinking about it? Here's what 50 agencies are getting from Flowfiy.' Show a results screenshot. | ₹60,000 |
| New LinkedIn audience | Expand ICP: target IT consulting firms + business consulting + recruitment firms. Test if they convert at same rate. | ₹40,000 |

## Agency Partnerships — Fast-Track Bulk Users

One agency reseller can bring 5-15 users overnight. This is the highest-leverage activity in Month 2.

| Action | Detail | Budget |
| --- | --- | --- |
| Close 5 agency partners | From the 20 BD leads sourced in Month 1: close 5 on a reseller deal. Offer 20% recurring MRR commission. They promote to their clients and networks. | ₹30,000 |
| Agency white-label pitch | For 2-3 larger agencies (50+ employees): offer white-label Flowfiy under their brand. They pay upfront for seats. Pricing: ₹15,000/month for 10 seats. | ₹20,000 |
| Partner kickoff kits | Create a simple 1-pager + demo video for each partner. Make it dead-easy for them to pitch Flowfiy to their clients. | ₹10,000 |
| Referral payout budget | Pay out first month of referral commissions to incentivise partners to keep pushing. | ₹40,000 |

## Hire a Sales VA + Events

| Action | Detail | Budget |
| --- | --- | --- |
| Part-time Sales VA | Hire a VA (Part-time, ₹15,000/month) to follow up on all Flowfiy-generated leads, book demo calls, and handle first-response to trial sign-up emails. | ₹30,000 |
| 2 startup events | Attend SaaS/startup meetups in Pune + 1 in Mumbai. Bring a printed 1-pager. Speak for 5 minutes if possible. Every conversation = a potential user. | ₹40,000 |
| YourStory / Inc42 pitch | Email YourStory + Inc42 journalists with a story angle: 'MIT-WPU student builds AI outbound tool that replaced his SDR.' Free PR. One feature = 300-500 trial signups. | ₹0 |
| Launch referral program | Give existing users: 1 month free for every user they refer. Announce via email + LinkedIn. Budget covers first-batch incentive payouts. | ₹20,000 |

| Month 2 Target | Users | MRR |
| --- | --- | --- |
| End of Day 60 | 175 paying users | ₹2,97,500/month |

MONTH 3 — CLOSE HARD (Days 61–90) Budget: ₹2,50,000

Objective: 350 paying users and ₹5.95L MRR. By Month 3, you have data, paying users, case studies, and proof. Use them aggressively. Spend drops — the machine is running.

Month 3 is about CONVERSION, not acquisition. You have a large trial base from Month 1-2. Close them.

## Convert the Trial Base

| Action | Detail | Budget |
| --- | --- | --- |
| Trial expiry campaign | 7 days before every trial expires: send 3-email urgency sequence. Day 7: 'Your trial ends soon.' Day 3: '3 days left — here's what you'll lose.' Day 0: '20% off your first month if you upgrade today.' | ₹0 |
| Personal close calls | VA + Ayush: call every trial user (100+) who is still unconverted. 10 minutes each. Close at 25% = 25 new users from this alone. | ₹0 (VA already hired) |
| Case study ads | Produce 2 written case studies with real customers. Run as LinkedIn ads: 'Agency X went from 0 to 200 outreach emails/day using Flowfiy.' | ₹40,000 (production + ad spend) |
| Retarget hard | Retarget all unconverted trials with urgency-based creative. Limited-time offer: 2 months for price of 1. | ₹40,000 |
| Upgrade existing users | Push INDIE users to STARTER. STARTER to GROWTH. A 30% upgrade rate on 175 users adds ₹1L+ MRR without new users. | ₹10,000 (email campaign) |

## New Acquisition + Churn Prevention

| Action | Detail | Budget |
| --- | --- | --- |
| Maintain paid ads (reduced) | Cut total ad spend by 40% vs Month 2. Only run campaigns with proven positive ROI. Free up budget for conversion activities. | ₹80,000 |
| Partner payouts Month 2 | Pay referral commissions from Month 2 partner activity. Incentivise them to keep going. | ₹50,000 |
| Churn intervention | For any user who cancels: immediate founder call. Offer 1 month free to stay. Understand why they're leaving and fix it. | ₹0 |
| Product: 1 retention feature | One high-impact feature that reduces churn: reply tracking dashboard or AI-suggested follow-up timing. Freelance dev, 1 sprint. | ₹40,000 |
| Reserve | Unexpected cost buffer. | ₹40,000 |
| Flowfiy self-outreach (ongoing) | Never stop. 3,000 outreach emails/month. This is the flywheel. Keep it running. | ₹20,000 |

| Month 3 Target | Users | MRR |
| --- | --- | --- |
| End of Day 90 | 350 paying users | ₹5,95,000/month |

# 6.  90-Day Revenue Projections

| Week | New Users | Total Users | MRR | Spend | Cumul. Spend |
| --- | --- | --- | --- | --- | --- |
| W1 | 3 | 3 | ₹5,100 | ₹55,000 | ₹55,000 |
| W2 | 7 | 10 | ₹17,000 | ₹1,10,000 | ₹1,65,000 |
| W3 | 15 | 25 | ₹42,500 | ₹1,00,000 | ₹2,65,000 |
| W4 | 25 | 50 | ₹85,000 | ₹85,000 | ₹3,50,000 |
| W5 | 35 | 85 | ₹1,44,500 | ₹1,10,000 | ₹4,60,000 |
| W6 | 40 | 125 | ₹2,12,500 | ₹1,00,000 | ₹5,60,000 |
| W7 | 30 | 155 | ₹2,63,500 | ₹1,00,000 | ₹6,60,000 |
| W8 | 20 | 175 | ₹2,97,500 | ₹90,000 | ₹7,50,000 |
| W9 | 40 | 215 | ₹3,65,500 | ₹80,000 | ₹8,30,000 |
| W10 | 45 | 260 | ₹4,42,000 | ₹70,000 | ₹9,00,000 |
| W11 | 45 | 305 | ₹5,18,500 | ₹60,000 | ₹9,60,000 |
| W12 | 45 | 350 | ₹5,95,000 | ₹40,000 | ₹10,00,000 |

By Week 10, monthly revenue (₹4,42,000 MRR) exceeds monthly spend. The machine becomes self-funding in Month 3. After 90 days, you no longer need the 10L — the business finances its own growth.

# 7.  Week-by-Week Checklist

Print this. Check off every item. If something is not done, it is costing you users.

| Week | Must-Complete Actions |
| --- | --- |
| W1 | Fix onboarding UX (freelancer hired Day 1). PostHog installed. Email drip set up. Apollo subscription active. Comparison landing page live. Flowfiy outreach running at 30 emails/day. |
| W2 | LinkedIn Ad Set A + B live. Google Search Ads live. 20 agency BD outreach messages sent via Flowfiy. WhatsApp outreach started (15/day). GST registration filed. |
| W3 | Check ad performance. Kill any set with CPL >₹1,000. Double budget on winner. Call every trial user personally. First agency BD follow-ups. |
| W4 | Close first 50 users. Scale winning ad set. Post 3 LinkedIn organic posts with real Flowfiy results. First case study draft started. Legal done. |
| Week | Must-Complete Actions |
| W5 | Scale best Month 1 ad channel. Retargeting campaign live. 5 agency partnership deals closed. Sales VA hired. YourStory + Inc42 pitch emailed. |
| W6 | Partner kickoff kits sent. Referral program announced to existing users. New LinkedIn audience test running. Expand Flowfiy outreach to 50 emails/day. |
| W7 | VA handling all trial follow-ups. Attend first startup event. Review agency partner results. Scale any white-label deals. |
| W8 | Close Month 2 at 175 users. Pay out first referral commissions. Case study 1 published. Begin retargeting with case study ad. |
| Week | Must-Complete Actions |
| W9 | Trial expiry urgency campaign live. Personal close calls on all unconverted trials. Upgrade campaign to existing users. Reduce paid ad spend by 40%. |
| W10 | Case study 2 published and running as ad. Attend second startup event. Check churn: call every cancellation personally. |
| W11 | Retention feature deployed (reply tracking). Partner payout Month 2. Identify top 20 users for testimonials/referrals. |
| W12 | Close at 350 users. ₹5.95L MRR. Document what worked for Month 4 onwards. The business is now self-funding. |

# 8.  Non-Negotiables — Rules for the 3-Month Sprint

| 1 | Flowfiy runs outreach every single day. No exceptions. 3,000 emails/month minimum. This is the cheapest, fastest, most authentic channel. Stop this and you've kneecapped the strategy. |
| --- | --- |
| 2 | Ayush closes the first 100 users personally. Not a VA. Not an email. A phone call. Personal founder calls convert at 3-5x the rate of email follow-ups. |
| 3 | Kill failing ad sets within 14 days. No attachment. If CPL > ₹1,000 after ₹20,000 spend: cut it. Move budget to what works. |
| 4 | Do NOT spend on SEO, YouTube, or long-form content. These are 6-month plays. You have 90 days. |
| 5 | Do NOT hire a full-time employee. 3 months is too short to onboard and get ROI. Use freelancers and VAs only. |
| 6 | Measure weekly, not monthly. By the time a monthly report shows a problem, you've burned 4 weeks. Review every Monday. |
| 7 | The referral program is only as good as your existing users' success. Make sure Month 1 users are actually getting results before pushing them to refer. |
| 8 | Reserve (₹70,000) is not for spending. It is for emergencies only. Treating it as bonus budget breaks the plan. |

# 9.  Warning Signs — When to Pivot Fast

If you see any of these by the dates shown, act immediately. Do not wait for the month to end.

| Warning Sign | By When | What to Do |
| --- | --- | --- |
| Less than 10 trial signups from ads | Day 14 | Pause ads. Rebuild ad copy and landing page. The problem is the message, not the channel. Test new angle: focus on pain ('losing deals to faster competitors?') instead of features. |
| Trial-to-paid conversion <10% | Day 21 | Onboarding is broken. Stop all acquisition spend until conversion rate is fixed. Adding users to a leaking funnel is burning money. |
| Less than 20 paying users | Day 30 | Reduce paid ads. Go 100% personal outreach. Ayush messages 50 founders per day on LinkedIn directly. Founder-to-founder beats ads at this stage. |
| Churn >10% in Month 1 | Day 45 | Product-market fit issue. Stop scaling. Interview every churned user same day they cancel. Fix the core problem before spending more. |
| No agency partner closed | Day 45 | Lower the barrier. Offer first month free to the agency. They don't have to pay — they just need to share Flowfiy with 5 clients. |
| MRR below ₹2L | Day 60 | Reallocate ₹1L from reserve + Month 3 budget to personal founder-led BD. Ayush attends 5 events in one month. Close deals in person. |

# 10.  90-Day Outcome Summary

| Paying Users | MRR | Total Spent | Monthly Profit |
| --- | --- | --- | --- |
| 350 | ₹5,95,000 | ₹10,00,000 | ~₹5,55,000 |

At end of Month 3: MRR = ₹5,95,000. Monthly infra + AI costs = ~₹40,000. Net = ₹5,55,000/month. The ₹10L is gone — but the business generates ₹5.5L+ every month without spending it. Payback period on the ₹10L investment: 2 months from Day 90.

Flowfiy  |  flowfiy.com  |  Ayush Saha  |  May 2026  |  Confidential